## EPIC Summary
Epic | PASSED | FAILED | BROKEN | SKIPPED | UNKNOWN | totalTests | passRate | status
NVHUB-5339: CDS UI Component Library - Migration | 3 | 0 | 0 | 0 | 0 | 3 | 100 | Acceptable
API Testing: GraphQL | 169 | 6 | 1 | 0 | 0 | 176 | 96.02 | Acceptable
INVHUB-1018: User/System Preferences | 1 | 0 | 0 | 0 | 0 | 1 | 100 | Acceptable
INVHUB-1035: Sensa Copilot for Investigators GA | 2 | 0 | 0 | 0 | 0 | 2 | 100 | Acceptable
INVHUB-10821: Filtering on transactions | 8 | 0 | 0 | 0 | 0 | 8 | 100 | Acceptable
INVHUB-9173: Abanca Technical POC | 2 | 0 | 0 | 0 | 0 | 2 | 100 | Acceptable
INVHUB-1180: Sensa Copilot enhancements/support(Q1) | 2 | 0 | 0 | 0 | 0 | 2 | 100 | Acceptable
INVHUB-8565: Refinements to event/audit log | 1 | 0 | 0 | 0 | 0 | 1 | 100 | Acceptable
INVHUB-4521: NFR - Security | 2 | 0 | 0 | 0 | 0 | 2 | 100 | Acceptable
INVHUB-13728: UI doc summary - Enterprise Knowledge Management | 4 | 0 | 0 | 0 | 0 | 4 | 100 | Acceptable
INVHUB-18: Authentication and Login | 5 | 0 | 0 | 0 | 0 | 5 | 100 | Acceptable
INVHUB-9919: (Phase 3) Workflow - Decision making and triggering conditional workflows | 11 | 1 | 0 | 0 | 0 | 12 | 91.67 | Maintenance Advised
INVHUB-290: Teams Management | 14 | 2 | 0 | 0 | 0 | 16 | 87.5 | Maintenance Advised
INVHUB-2452: Enhancements to the investigator experience | 178 | 0 | 8 | 28 | 0 | 214 | 83.18 | Maintenance Advised
INVHUB-9920: Tag Category (workflow) | 10 | 0 | 2 | 0 | 0 | 12 | 83.33 | Maintenance Advised
API Testing | 202 | 21 | 4 | 13 | 0 | 240 | 84.17 | Maintenance Advised
INVHUB-13708: Transaction Ingestion Phase 1 | 9 | 1 | 0 | 0 | 0 | 10 | 90 | Maintenance Advised
INVHUB-171: Data Access - GA | 0 | 1 | 15 | 0 | 0 | 16 | 0 | Review Required
INVHUB-9920: Maintenance of Tags and Tag Categories | 52 | 12 | 12 | 0 | 0 | 76 | 68.42 | Review Required
INVHUB-1047: Subject Centric Investigation - TM | 4 | 0 | 4 | 0 | 0 | 8 | 50 | Review Required
INVHUB-966: Open Investigations queue/list (GA) | 0 | 4 | 0 | 0 | 0 | 4 | 0 | Review Required
INVHUB-11621: Provide detailed analysis at the individual detection level | 34 | 6 | 12 | 4 | 0 | 56 | 60.71 | Review Required
INVHUB-8981: Narrative contribution and UI view | 3 | 1 | 0 | 0 | 0 | 4 | 75 | Review Required
INVHUB-11811: Prefill transactions on the transaction tab | 12 | 11 | 0 | 0 | 0 | 23 | 52.17 | Review Required
INVHUB-8114: Authentication | 28 | 5 | 10 | 0 | 0 | 43 | 65.12 | Review Required
INVHUB-7367: IH Bugs | 1 | 3 | 4 | 0 | 0 | 8 | 12.5 | Review Required
INVHUB-5: Open Investigations List | 0 | 4 | 0 | 0 | 0 | 4 | 0 | Review Required
INVHUB-5339: CDS UI Component Library - Migration | 0 | 0 | 1 | 0 | 0 | 1 | 0 | Review Required
INVHUB-4976: Data Access - Q2 | 4 | 0 | 36 | 0 | 0 | 40 | 10 | Review Required
INVHUB-11963: Copilot: Add some more complex and standard queries for Transactions | 5 | 8 | 0 | 0 | 0 | 13 | 38.46 | Review Required
INVHUB-3309: Investigation Hub Tags | 52 | 12 | 12 | 0 | 0 | 76 | 68.42 | Review Required
INVHUB-3120: Workflows -Manager creation of Actions / map to teams | 68 | 28 | 13 | 0 | 0 | 109 | 62.39 | Review Required
INVHUB-126: Entity Centric Investigation (Subject Details) (MVP) | 10 | 10 | 13 | 15 | 0 | 48 | 20.83 | Review Required
INVHUB-2377: Roles Management Q1 | 23 | 5 | 6 | 0 | 0 | 34 | 67.65 | Review Required
INVHUB-13905: (Phase 2) Workflow Actions mgmt | 24 | 6 | 2 | 0 | 0 | 32 | 75 | Review Required
INVHUB-2136: Subject Centric Investigation(Q1) | 1 | 1 | 0 | 0 | 0 | 2 | 50 | Review Required
INVHUB-13: Menu and User Administration | 4 | 3 | 3 | 0 | 0 | 10 | 40 | Review Required
INVHUB-157: Assign (Reassign) and drill down (GA) | 1 | 1 | 0 | 0 | 0 | 2 | 50 | Review Required
INVHUB-2168: Teams Management - Q1 | 4 | 4 | 0 | 0 | 0 | 8 | 50 | Review Required
TOTAL | 953 | 156 | 158 | 60 | 0 | 1327